## Sheet1
Product Backlog Attendance Marking for Classroom Project ID: A001 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | User Registration | User | As a user I want the system that procure the fundamental details of the user | 1-When the user clicks on the registration link, it should re-direct to registration form. 2-User needs to fill some of the basic attributes/fields like : First Name, Last Name, Employee Id, Email, Password. Employee Id should be an autogenerated field. Clicking ‘Submit’ should validate the datatype constraints for each field 3-User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Post-successful field level validation, save the information in the database 5-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Critical
US_2 | User Authentication | User | As a User I want the system that authenticate the user credentials of the registered user | 1-A registered user – is able click ‘Login’ link, after keying in ‘Employee Id & ‘Password’ field and get his credentials authenticated with the existing database entry. 2-If a registered user – is unable to login and get his credentials authenticated, The user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical
US_3 | Admin Registration | Admin | As a User I want the system to procure the fundamental details of the admin | 1-When the Admin clicks on the registration link, it should re-direct to registration form. 2-Admin needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, Admin Id, Password. Admin Id should be auto generated. Clicking ‘Submit’ should validate the datatype constraints for each field 3-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Post-successful field level validation, save the information in the database 5-Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Critical
US_4 | Admin Authentication | Admin | As an Admin I want the system to authenticate the user credentials of the registered Admin | 1-A registered Admin – is able click ‘Login’ link, after keying in ‘Admin ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_5 | Admin Registration approval | Admin | As an Admin I want the system to allow the super user to approve / reject the Admin registration | 1-Super User should be able to approve / reject Admin registration. 2-Upon approval, Admin should be able to log in successfully. 3-When the Super user Approves/Rejects, the status should be updated in the database. 4-If the Approval is pending or rejected, Message should be displayed when Admin tries to log in. 5-Super User can be a preloaded user id and Password in the database who can approve Admin registration | Critical
US_6 | Add trainer details | Admin | As an Admin I want the system to allow Admin to add the trainer details | 1-When the Admin clicks on the add trainer link, it should re-direct to Add Trainer page. 2-Admin needs to fill some of the basic attributes/fields as mentioned be: Session ID, Session description, Skill set, Time, Session date, Session time, Available slots etc. 3-Admin needs to fill some of the basic attributes/fields as mentioned like -Trainer ID, Trainer Name, Contact number, Email, Skill set 4-Clicking ‘Submit’ should validate the datatype constraints for each field 5-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red Post-successful field level validation, save the information in the database 6- Trainees can add/neglect few fields if appropriate. | Critical
US_7 | Add session details | Admin | As an Admin I want the system to allow Admin to add the session details | When the Admin clicks on the add session link, it should re-direct to Session addition page. Admin needs to fill some of the basic attributes/fields as mentioned below in requirement: Session ID, Session description, Skill set, Session date, Session time, Available slots Clicking ‘Submit’ should validate the datatype constraints for each field Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red Post-successful field level validation, save the information in the database Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Critical
US_8 | Update trainer details | Admin | As an Admin I want the the system to allow Admin to update the trainer details | When the Admin clicks on the Update trainer link, it should list all the available trainer details. On clicking the Trainer ID, system should display the details of the selected trainer. Admin should be able to update the details of the trainer. There should be option to delete the record. Clicking ‘Submit’ should validate the datatype constraints for each field and save the details to the database. | Medium
US_9 | Update session details | Admin | As an Admin I want the system to allow Admin to update the session details | When the Admin clicks on the Update session link, it should list all the available session details. On clicking the Session ID, system should display the details of the selected session. Admin should be able to update the details of the session. There should be option to delete the record. Clicking ‘Submit’ should validate the datatype constraints for each field and save the details to the database. | Medium
US_10 | Add skill set | Admin | As an Admin I want the system to allow admin to add the skill set | Admin on clicking Add Skills should redirect to the Skills Addition page. Admin needs to fill some of the basic attributes/fields as mentioned below in requirement: Skill ID, Skill type, Skill Description Clicking ‘Submit’ should validate the datatype constraints for each field Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red Post-successful field level validation, save the information in the database Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Critical
US_11 | Map skill set to the sessions | Admin | As an Admin I want the system to allow Admin to map the skill set to the available sessions | Admin on clicking Map Skills should redirect to the Skills Mapping page. Admin needs to fill some of the basic attributes/fields as mentioned below in requirement: Skill ID, Session ID Clicking ‘Submit’ should validate the datatype constraints for each field Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red Post-successful field level validation, save the information in the database Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Medium
US_12 | View the available session details | User | As an User I want the system to allow User to view the available sessions | User on clicking Sessions should redirect to the Sessions page. Session’s page should list all the available Session Ids and Description Clicking Session ID should display all the details | Medium
US_13 | Skill based / session id search for session | User | As an User I want the system to allow the user to search for the session based on the skill / session id. | User should have the option to search for the sessions based on the skills. User should have the option to search for the sessions based on the session id. | Medium
US_14 | Enroll for session | User | As an User I want the system to allow user to enroll for the session | Clicking Session ID should display all the details. There should be an option for enrollment Upon enrollment user should get a notification. Notification can be a message displayed in the Users' home page / notification page. | Critical
US_15 | Approve enrollment | Admin | As an Admin I want the system to allow Admin to approve the enrollment | Admin on clicking, Enrollment request link, should display all the enrollment request for approval. Admin can approve or reject the request Once approved / rejected notification should be triggered to User which should be viewed by User in the notification page The status of the approval should be updated in the DB | Medium
US_16 | Send remainders | User | As an User I want the system to send remainders to the user 2 days prior to the session. | 1-After enrollment, User should be sent remainder 2 days prior to the session date. 2-Reminder should be displayed in the User home page when he logs in or can be in notification page. | Low
US_17 | Attendance marking | User | As an User I want the system to allow Users mark attendance on launch the session | User should be able to mark the attendance on the day of the session | Low
US_18 | Admin Report | Admin | As an Admin I want the system to get the report of the available learnings, Number of users taken the learning, feedback reports. | When Admin clicks, Reporting link, It should list Class room session / virtual session On clicking Class room session, it should display all the available Class room session code On clicking the Session ID, it should display the details of number of users taken the course, Feedback on the course content. Admin should have option to display all the course or skill based. | Low
US_19 | User report | User | As an User I want the system to list the completed course details for the User login with the score. | When User clicks, Session Report link, It should list all the Sessions attended by the user. | Low
US_20 | User feedback | User | As an User I want the system to pop up feedback to the user upon completion of the course. | Admin should have the option to update the Feedback question for each session present in the system When the user completes the session, it should redirect to the feedback form and the user need to fill and submit. | Low
US_21 | Feedback Report | Admin | As an Admin I want the system to generate report on the course based on the Learner feedback. | Admin on clicking feedback report link, it should display all the available Sessions On selecting the session, the feedback result should be displayed. Admin should be able to search based on skill Admin should be able to search based on session code. | Low
US_22 | Add Feedback form | Admin | As an Admin I want the system to allow Admin to add feedback form for the Course / Assessment | When Admin clicks add Feedback, it should display all the assessment available in the system On clicking the assessment code, it should redirect to the Feedback form Admin should be able to fill in the Questions and the ratings | Low
US_23 | Other validations | User | As an User I want the system to allow add on validations like Forget User ID, Forget Password | During registration, System should pop up three secret questions for Password recovery. Email id and contact number can also be used along with the secret questions to uniquely identify the User as Same answers can be given by many users When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. When the user clicks Forgot Password, system should ask for the User ID and secret questions. On answering the questions correctly, the password reset page should be displayed. On entering the details in the password reset page, password should be validated On clicking Submit, the details should be saved to the Database | Low
US_24 | Logoff | User/Admin | As an User / Admin I want to log off from the system | System should disconnect on clicking Log off. | Critical